## UPS Functionalities
United Production System - Functionalities
Specific Functionality | General Functionality | Phase | Initial Agreement | Developed | Comments
User with View Restrictions | General System Settings | 1 | √ | √
Printable Reports | General System Settings | 1 | X | √
Warehouse - Materials | Inventory and Stock | 1 | √ | √
Warehouse - Consumables | Inventory and Stock | 1 | √ | √ | Match with real stock
Warehouse - Master Batch | Inventory and Stock | 1 | √ | √ | Match with real stock
Warehouse - Ink and Solvents | Inventory and Stock | 1 | √ | √ | Match with real stock
Warehouse - Semifinished products | Inventory and Stock | 1 | √ | -
Warehouse - Finished products | Inventory and Stock | 1 | √ | -
Sacks (Extruder, Cutting, Packaging) | Inventory and Stock | 1 | √ | √
Multilayer (Rajio) | Inventory and Stock | 1 | √ | √
Printing (Printing & Slitting) | Inventory and Stock | 1 | √ | √
Injection | Inventory and Stock | 1 | √ | √
Macchi | Inventory and Stock | 1 | √ | √
Packing Bags (Extruder, Printing, Cutting) | Inventory and Stock | 1 | √ | √
Balance Stock | Inventory and Stock | 1 | X | √
Warehouse | Material Consumption Monitoring (Opening, Closing) | 1 | √ | √ | Material, Inks, Consumables, Master Batch
Sacks (Extruder, Cutting, Packaging) | Material Consumption Monitoring (Opening, Closing) | 1 | √ | √
Multilayer (Rajio) | Material Consumption Monitoring (Opening, Closing) | 1 | √ | -
Printing (Printing & Slitting) | Material Consumption Monitoring (Opening, Closing) | 1 | √ | -
Injection | Material Consumption Monitoring (Opening, Closing) | 1 | √ | -
Macchi | Material Consumption Monitoring (Opening, Closing) | 1 | √ | -
Packing Bags (Extruder, Printing, Cutting) | Material Consumption Monitoring (Opening, Closing) | 1 | √ | -
Remarks and Downtimes per machine | Reports Production | 1 | X | √
Report Production | Reports Production | 1 | √ | √
Report Waste | Reports Production | 1 | √ | √
Report Raw Material Consumption | Reports Production | 1 | √ | √
Report Target Achievements | Reports Production | 1 | √ | √
Report Remarks and Downtimes | Reports Production | 1 | √ | √
Sacks (Extruder, Cutting, Packaging) | Real Time Production Monitoring (Entries Production Reports) | 1 | √ | √
Multilayer (Rajio) | Real Time Production Monitoring (Entries Production Reports) | 1 | √ | √
Printing (Printing & Slitting) | Real Time Production Monitoring (Entries Production Reports) | 1 | √ | √
Injection | Real Time Production Monitoring (Entries Production Reports) | 1 | √ | √
Macchi | Real Time Production Monitoring (Entries Production Reports) | 1 | √ | √
Packing Bags (Extruder, Cutting) | Real Time Production Monitoring (Entries Production Reports) | 1 | √ | √
Records of repairs in machines and cost related to machines maintenance | Machine Maintenance | 2 | √ | X
Alert to order Raw Material (purchasing dates calculating arrival times) | Purchasing | 2 | √ | X
Track of Raw Material Imports | Purchasing | 2 | X | √ | UD
Track of Local Purchases & Loans | Purchasing | 2 | X | √ | UD
Printing Production Plan | Sales Orders | 2 | X | X
Macchi Production Plan | Sales Orders | 2 | X | X
Track Sales Orders & delays | Sales Orders | 2 | X | X
Track of movements from production - warehouse to supply | Dispatch | 3 | X | X
Daily Automatic Backups | General System Settings | 3 | X | X
Log out after 30 sec | General System Settings | 3 | X | X
Second UPS system | General System Settings | 3 | X | X
Cost of Warehouse | General System Settings | 3 | X | X
Machines Spare Parts | Inventory and Stock | 3 | X | √
Traceability of rolls | Real Time Production Monitoring | 3 | X | X
Track of reprocess material | Real Time Production Monitoring | 3 | X | X
Note on A48: Administrator: Copy of UPS with automatic different production and finished goods values.